DR. TEBEILA DENTAL PRACTICE

STRATEGIC ACTION PLAN  |  2026

Coachee: Dr. Founa Tebeila  ·  Plan Start Date: 27 March 2026

Short Term: 3 months (by end Jun 2026)  ·  Medium Term: 6 months (by end Jul 2026)  ·  Long Term: 12 months (by end Mar 2027)

## 1. EXECUTIVE SUMMARY

This Strategic Action Plan provides Dr. Founa Tebeila with a structured, time-bound roadmap to consolidate and grow her dental practice portfolio. The plan addresses three interconnected dental practices and covers governance, human resources, marketing and operational transformation across three planning horizons.

The plan is grounded in nine core milestones derived from the coaching engagement, with clearly defined functional areas, owners and BRAG-GP tracking. Successful execution will result in a legally registered trade name, formalised partnerships, competent practice administration, an active digital marketing presence, and a rationalised three-practice portfolio.

## 2. VISION, MISSION & STRATEGIC OBJECTIVES

| VISION | MISSION | CORE VALUES |
| --- | --- | --- |
| To become the leading multi-practice dental brand in the region, delivering world-class oral healthcare through ethical governance, empowered teams and innovation. | To provide accessible, high-quality dental care across multiple practices while building a sustainable, professionally governed and commercially successful dental group. | Excellence · Integrity · Patient-Centricity · Collaboration · Accountability |

Strategic Objectives

- Establish a legally compliant and branded dental group structure (Governance)

- Formalise partnership agreements for all three practices (Governance)

- Build a high-performance, buy-in-driven team across all practices (HR)

- Appoint capable administrative leadership to free clinical time (HR)

- Build a consistent, growth-oriented digital brand presence (Marketing)

- Rationalise the practice portfolio — exit the Nando's practice (Operations)

- Develop and execute individual roadmaps for each of the three practices (Leadership)

## 3. STRATEGIC CONTEXT & KEY DRIVERS

Before individual practice roadmaps can be executed, the following key drivers must be diagnosed and understood for all three dental practices:

| DRIVER | DESCRIPTION | IMPLICATION FOR STRATEGY |
| --- | --- | --- |
| Revenue & Profitability | Current revenue base, patient volumes, treatment mix and margins per practice. | Identify which practices are sustainable and which require intervention or exit. |
| Patient Base & Loyalty | Size, demographics, retention rate and referral patterns of existing patient base. | Informs marketing focus and where to invest in patient experience improvements. |
| Team Capacity & Culture | Staff skills, morale, retention risk and alignment with the practice vision. | Drives HR priorities — buy-in campaigns, training, and the practice administrator hire. |
| Competitive Landscape | Proximity of competing practices, service differentiation and pricing positioning. | Shapes the social media and brand strategy to highlight unique value. |
| Regulatory & Compliance | HPCSA compliance, practice registration, partnership structures and trade name rules. | Urgent governance actions — trade name registration and deregistration of Nando's practice. |
| Infrastructure & Technology | Equipment age, digital systems (practice management software, X-ray, sterilisation). | Roadmap investment priorities per practice; potential to attract referrals through modernisation. |

## 4. SMART GOALS ACTION PLAN — FULL MILESTONE TABLE

BRAG-GP Legend:  B = Achieved/Closed (Blue)  ·  G = On Track (Green)  ·  A = Requires Attention (Amber)  ·  R = In Jeopardy (Red)  ·  P = Postponed (Purple)  ·  Grey = Not Yet Started

| # | MILESTONE | FUNCTIONAL AREA | SHORT TERM (by 26 Jun 2026) | MEDIUM TERM (by 31 Jul 2026) | LONG TERM (by 27 Mar 2027) | BRAG-GP STATUS |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Register Dr. Tebeila Dental Studio Trade Name | Governance | Research CIPC requirements & check name availability (Apr 2026) | Submit CIPC registration application (May 2026) | Receive registration certificate & update all branding (Jun 2026) | Grey |
| 2 | Identify Key Drivers for the Three Dental Practices | Leadership | Conduct practice audits: financial, HR, patient volume (Apr 2026) | Compile consolidated key driver report per practice (May 2026) | Embed driver KPIs into practice scorecards (Jul 2026) | Grey |
| 3 | Develop Roadmaps for the Three Dental Practices | Leadership | Draft individual roadmaps based on key driver analysis (May 2026) | Present & agree roadmaps with practice leads (Jun 2026) | Quarterly roadmap review cadence established (Oct 2026) | Grey |
| 4 | Compile Partnership Agreement with Dr. Nape | Governance | Engage attorney; draft term sheet for Dr. Nape agreement (Apr 2026) | Review, negotiate and finalise agreement (Jun 2026) | Signed agreement executed & filed (Jul 2026) | Grey |
| 5 | Compile Partnership Agreement with Dr. Seabi | Governance | Draft term sheet for Dr. Seabi; align on equity/profit share (Apr 2026) | Review, negotiate and finalise agreement (Jun 2026) | Signed agreement executed & filed (Jul 2026) | Grey |
| 6 | Deregister the Nando's Practice | Governance | Obtain deregistration requirements from HPCSA & CIPC (Apr 2026) | Submit deregistration application; notify all stakeholders (Jun 2026) | Deregistration confirmed; assets/records transferred (Sep 2026) | Grey |
| 7 | Appoint a Practice Administrator | HR | Draft job profile; post vacancy & begin shortlisting (Apr 2026) | Conduct interviews; make appointment offer (May 2026) | Administrator inducted & fully operational (Jul 2026) | Grey |
| 8 | Solicit Current Team Buy-in | HR | Run team engagement sessions across all three practices (Apr 2026) | Address concerns; implement quick-win improvements (May 2026) | Measure engagement; embed culture in onboarding (Sep 2026) | Grey |
| 9 | Roll Out a Social Media Strategy | Marketing | Define brand voice, platforms (FB, IG, Google) & content calendar (Apr 2026) | Go live on all platforms; first 8 weeks of content posted (Jun 2026) | Monthly analytics review; 500+ followers; active reviews programme (Mar 2027) | Grey |

## 5. SHORT-TERM ROADMAP (27 Mar – 26 Jun 2026)

Focus: Foundation, Compliance & Quick Wins. Priority is to complete all governance pre-requisites, begin the administrator search, launch social media and run team buy-in sessions.

| MONTH | KEY ACTIONS | OWNER | DELIVERABLE | SUCCESS INDICATOR |
| --- | --- | --- | --- | --- |
| March 2026 (Kick-off) | • Finalise coaching plan • Brief legal counsel on trade name & partnerships • Schedule practice audits | Dr. Tebeila + Coach | Signed engagement letter with attorney | Legal brief issued by 31 Mar |
| April 2026 | • Conduct audits across 3 practices • Begin CIPC trade name search • Launch job posting for Administrator • Run first team buy-in session • Draft social media brand guide | Dr. Tebeila + Practice Teams | Audit reports; job advert live; brand guide v1 | All audit data collected; 1 team session done |
| May 2026 | • Draft partnership agreements (Nape & Seabi) • Shortlist & interview Administrator candidates • Post first social media content • Begin CIPC/HPCSA deregistration process for Nando's | Dr. Tebeila + Attorney + Marketing Lead | Draft agreements; social media live; candidate shortlist | Agreements in review; 2 posts per week live |
| June 2026 | • Finalise & sign both partnership agreements • Make Administrator appointment • Submit trade name registration • Deregistration application submitted • Second team buy-in session | Dr. Tebeila + Attorney + HR | Signed agreements; appointment letter; CIPC application | Both agreements signed; Administrator appointed |

## 6. MEDIUM-TERM ROADMAP (Jul 2026)

Focus: Stabilisation & Operational Excellence. Governance actions are completed. The practice administrator is operational. Social media is gaining traction. Practice roadmaps are agreed and being executed.

| MILESTONE | ACTIONS | DELIVERABLE | KPI / TARGET |
| --- | --- | --- | --- |
| Practice Administrator Fully Operational | Complete handover, set KPIs, introduce to all practice stakeholders and systems. | 30-60-90 day induction plan in place | Admin handling 80% of non-clinical tasks by end Jul |
| Practice Roadmaps Launched | Present individual roadmaps to each practice team; incorporate feedback; publish version 1. | 3 signed-off practice roadmaps | All practice teams briefed and aligned |
| Social Media Growth Phase | Increase posting frequency; launch Google review campaign; explore paid boosts. | 4+ posts/week across platforms; 200+ followers | Steady follower growth; minimum 10 new Google reviews |
| Trade Name & Deregistration Progress | Monitor CIPC registration; follow up on Nando's deregistration confirmation. | Updated CIPC correspondence on file | Trade name registered or confirmation received |
| Team Engagement Measurement | Deploy short team pulse survey across all 3 practices; analyse results. | Pulse survey results report | Minimum 70% positive engagement score |

## 7. LONG-TERM ROADMAP (Aug 2026 – Mar 2027)

Focus: Growth, Brand Building & Portfolio Optimisation. All governance foundations are in place. The focus shifts to growing the patient base, optimising each practice and exploring further expansion opportunities.

| STRATEGIC PRIORITY | TIMEFRAME | KEY INITIATIVES | SUCCESS METRICS |
| --- | --- | --- | --- |
| Brand & Marketing Growth | Aug – Dec 2026 | • Quarterly social media campaigns • Launch referral rewards programme • Explore website development • Consider Google Ads for new patient acquisition | 500+ followers across platforms; 25%+ growth in new patient enquiries; 4.5★ average Google rating |
| Practice Performance Optimisation | Aug – Dec 2026 | • Monthly practice performance reviews against roadmaps • Introduce patient feedback system • Identify and address service gaps per practice | Revenue growth of 15%+ across the group; patient satisfaction score 4/5+ |
| People & Culture | Sep – Nov 2026 | • Annual performance reviews for all staff • Identify staff development / CPD opportunities • Formalise HR policies and employment contracts | 100% staff with signed contracts; CPD plan in place for all clinical staff |
| Governance & Compliance Review | Oct – Nov 2026 | • 6-month review of partnership agreement performance • HPCSA compliance audit across all active practices • Update practice policies and protocols | Zero compliance findings; partnerships tracking to agreed terms |
| Portfolio Strategy Review | Jan – Mar 2027 | • Assess financial performance of each practice post-restructuring • Evaluate potential for 4th practice or further growth • Review and refresh 12-month strategic plan | Clear decision on portfolio — grow, consolidate or divest; next 12-month plan ready by Mar 2027 |

## 8. RISK REGISTER

| RISK | DESCRIPTION | LIKELIHOOD | IMPACT | MITIGATION |
| --- | --- | --- | --- | --- |
| Partnership Disagreement | Dr. Nape or Dr. Seabi resist proposed agreement terms | Medium | High | Engage experienced healthcare attorney early; use neutral mediator if needed; align on non-negotiables upfront. |
| Administrator Hire Delay | Suitable candidate not found within the 3-month window | Medium | Medium | Start recruitment immediately; consider interim contractor; widen search to include healthcare admin specialists. |
| Team Resistance to Change | Staff at one or more practices resist the new direction | Medium | High | Proactive buy-in sessions; transparent communication; address concerns promptly; involve key team members in roadmap design. |
| CIPC / HPCSA Delays | Government registration processes take longer than anticipated | High | Medium | Submit applications early; use a registered professional to assist; have parallel actions progressing so plan is not blocked. |
| Social Media Traction Slow | Low engagement on new social media platforms | Medium | Low | Set realistic expectations; invest in modest paid promotion; focus on quality content; leverage existing patient network for reviews. |
| Practice Revenue Pressure | One or more practices underperform financially during transition | Medium | High | Monthly financial reviews; early identification of at-risk practice; consider temporary fee review or promotion campaign. |

## 9. GOVERNANCE, TRACKING & REVIEW CADENCE

To ensure this plan remains live and actionable, the following review governance structure is proposed:

| REVIEW TYPE | FREQUENCY | PARTICIPANTS | PURPOSE |
| --- | --- | --- | --- |
| Coaching Check-in | Bi-weekly | Dr. Tebeila + Coach | Track milestone progress; address blockers; update BRAG-GP status on action plan. |
| Practice Leadership Meeting | Monthly | Dr. Tebeila + Practice Administrator + Practice Leads | Review individual practice roadmaps; discuss team issues; review financial performance. |
| Partnership Review | Quarterly | Dr. Tebeila + Dr. Nape + Dr. Seabi + Attorney | Review partnership agreement compliance; address any concerns; align on shared goals. |
| Strategic Plan Review | Quarterly (Jun, Sep, Dec 2026; Mar 2027) | Dr. Tebeila + Coach | Full review of strategic plan; update milestones; reprioritise if required; prepare for next planning horizon. |
| Social Media & Marketing Review | Monthly | Dr. Tebeila + Marketing Lead | Analyse analytics; review content calendar; adjust strategy based on performance. |

## 10. CONCLUSION & COMMITMENT

This Strategic Action Plan represents a clear and achievable path for Dr. Founa Tebeila to transform her dental practice portfolio from its current state into a structured, professionally governed and commercially successful multi-practice dental group.

The plan is designed to be a living document — reviewed, updated and owned by Dr. Tebeila. Its success depends on disciplined execution, proactive stakeholder engagement, and a commitment to building a high-performance team culture across all three practices.

| COACHEE SIGN-OFF | COACH / FACILITATOR SIGN-OFF |
| --- | --- |
| Name: Dr. Founa Tebeila Date: ___________________________ Signature: _______________________ | Name: ___________________________ Date: ___________________________ Signature: _______________________ |